## Tasks
Track | Owner | Phase | Task # | Task | Status | Dependencies / Notes
C - Data/Content/Platform | Alan | 0. Setup | 1 | Create repo structure (/frontend, /backend, /docs) | Done | All three agree on structure Week 1
C - Data/Content/Platform | Alan | 0. Setup | 2 | Provision Supabase project (Postgres + Storage) | Done
C - Data/Content/Platform | Alan | 0. Setup | 3 | Get MyScript iink API keys | Done
C - Data/Content/Platform | Alan | 0. Setup | 4 | Set up hosting accounts (Vercel, Railway/Render) | Done
C - Data/Content/Platform | All | C - Data/Content/Platform | 5 | C - Data/Content/Platform | In Progress | I suggest to just use private api call for access
C - Data/Content/Platform | All | 1. Data Layer | 7 | Write SQL migrations / table definitions | Not Started | Depends on #6
C - Data/Content/Platform | Richard | 1. Data Layer | 8 | Seed problems table (~20-30 problems), sourced via school contacts | Not Started | Leverage school relationship for real curriculum content
C - Data/Content/Platform | Jeff | 1. Data Layer | 9 | Seed misconception_rules and hints with first batch | Not Started | Coordinate wording/format with Dev B
C - Data/Content/Platform | All | 1. Data Layer | 10 | Enable Supabase Row Level Security policies | Not Started
C - Data/Content/Platform | All (led by C) | Sync | 11 | Week 1: agree API contract / Pydantic schema across all 3 tracks | In Progress | Hard sync point - do before splitting off, see doc at math-tutor-mvp/docs/api_contract_draft_20260728.md
C - Data/Content/Platform | All | 11. Security | 47 | Enforce HTTPS everywhere | Not Started
C - Data/Content/Platform | Alan | 11. Security | 48 | Keep MyScript/Supabase keys server-side only | Done
C - Data/Content/Platform | Alan | 11. Security | 49 | Store LaTeX only, not raw ink strokes, by default | Not Started
C - Data/Content/Platform | Alan | 11. Security | 50 | Add simple student access code | Not Started | Tied to UI
C - Data/Content/Platform | All | 11. Security | 51 | Tighten Supabase RLS policies once access code exists | Not Started | Depends on #50
C - Data/Content/Platform | All | 12. Testing/QA | 54 | Organize manual QA with real kids' handwriting via school | Not Started | Dev A + B support
C - Data/Content/Platform | Richard | 12. Testing/QA | 55 | Verify curriculum coverage vs SLO tussendoelen groep 7/8 | Not Started
C - Data/Content/Platform | All | 13. Deployment | 56 | Deploy backend to Railway/Render, connect Supabase | Not Started | Depends on B's backend
C - Data/Content/Platform | Alan | 13. Deployment | 57 | Deploy frontend to Vercel, point at backend API URL | Not Started | Depends on A's frontend
C - Data/Content/Platform | All | 13. Deployment | 58 | Smoke-test production environment end-to-end | Not Started
C - Data/Content/Platform | Dev C (Leader) | 13. Deployment | 59 | Set up monitoring / error logging (e.g. Sentry) | Not Started
C - Data/Content/Platform | Richard | 14. Content | 60 | Expand problem bank across all rekenen domains | Blocked | Post-MVP not relavant for now
C - Data/Content/Platform | Jeff | 14. Content | 61 | Expand misconception rule library from real usage data | Blocked | Post-MVP not relavant for now
C - Data/Content/Platform | Jeff | 14. Content | 62 | Iterate hint wording based on observed confusion | Blocked | Post-MVP not relavant for now
C - Data/Content/Platform | All | 1. Data Layer | 6 | Design Supabase schema: problems, attempts, attempt_steps, misconception_rules, hints | Not Started | Blocks B's DB client work
B - Backend/Math Engine | All | 2. Backend Skeleton | 12 | Scaffold FastAPI project with Pydantic models | Not Started | Depends on #11 API contract
B - Backend/Math Engine | All | 2. Backend Skeleton | 13 | Set up Supabase Python client / DB connection layer | Not Started | Depends on #6/#7
B - Backend/Math Engine | Richard | 2. Backend Skeleton | 14 | Implement GET /problems/{id} | Not Started
B - Backend/Math Engine | Richard | 2. Backend Skeleton | 15 | Implement POST /attempts (persist attempt + steps) | Not Started
B - Backend/Math Engine | All | 2. Backend Skeleton | 16 | Add error handling, validation, logging | Not Started
B - Backend/Math Engine | Alan | 3. Recognition | 18 | Build Recognition Service wrapper around MyScript API | Not Started | Depends on #3 API keys
B - Backend/Math Engine | Alan | 3. Recognition | 19 | Implement POST /recognize endpoint | Not Started
B - Backend/Math Engine | Alan | 3. Recognition | 21 | Handle low-confidence recognition (flag for confirmation) | Not Started
B - Backend/Math Engine | Alan | 4. Math Parser | 22 | Implement LaTeX to SymPy expression parsing | Not Started
B - Backend/Math Engine | Alan | 4. Math Parser | 23 | Build canonical-form normalizer | Not Started
B - Backend/Math Engine | Alan | 4. Math Parser | 24 | Unit test parser: fractions, mixed numbers, decimals, negatives | Not Started
B - Backend/Math Engine | Jeff | 5. Step Evaluator | 25 | Implement expression validity check | Not Started
B - Backend/Math Engine | Jeff | 5. Step Evaluator | 26 | Implement internal math correctness check | Not Started
B - Backend/Math Engine | Jeff | 5. Step Evaluator | 27 | Implement transition validity check (legal derivation) | Not Started
B - Backend/Math Engine | Jeff | 5. Step Evaluator | 28 | Return structured EvaluationResult per step | Not Started
B - Backend/Math Engine | Jeff | 6. Misconception Detector | 29 | Define rule format for misconception_rules | Not Started | Coordinate with Dev C on content
B - Backend/Math Engine | Jeff | 6. Misconception Detector | 30 | Implement rule-matching engine | Not Started | Needs seed rules from #9
B - Backend/Math Engine | Jeff | 6. Misconception Detector | 31 | Return misconception_id or null fallback | Not Started
B - Backend/Math Engine | Jeff | 7. Tutor/Hint Service | 33 | Map misconception_id to approved hint message | Not Started | Needs seed hints from #9
B - Backend/Math Engine | Jeff | 7. Tutor/Hint Service | 34 | Implement fallback generic hint | Not Started
B - Backend/Math Engine | Jeff | 7. Tutor/Hint Service | 35 | Decide hint tone/language (Dutch, age-appropriate) | Not Started | Dev C validates with school
B - Backend/Math Engine | Dev B | 8. Orchestration | 36 | Implement pipeline: receive -> recognize -> parse -> validate -> detect -> return | Not Started
B - Backend/Math Engine | Dev B | 8. Orchestration | 37 | Wire POST /attempts/check to full pipeline | Not Started
B - Backend/Math Engine | Dev B | 8. Orchestration | 38 | Add timing/logging at each pipeline stage | Not Started
B - Backend/Math Engine | Dev B | 12. Testing/QA | 52 | Unit tests: parser, evaluator, misconception matcher | Not Started
B - Backend/Math Engine | Dev B | 12. Testing/QA | 53 | Integration tests: full /attempts/check pipeline | Not Started
A - Frontend | Alan | 0-3. Client Setup | 1b | Scaffold Next.js + Tailwind project | Done | Depends on #1 repo structure, PR is pending.
A - Frontend | Alan | 3. Recognition (client) | 17 | Integrate MyScript iink Web SDK for ink capture | Not Started | Depends on #3 API keys
A - Frontend | Alan | 3. Recognition (client) | 20 | Add manual Edit fallback for recognized LaTeX | Not Started
A - Frontend | Alan | 9. Frontend Client | 39 | Build problem display component (question + KaTeX) | Not Started
A - Frontend | Alan | 9. Frontend Client | 40 | Build step-entry UI: rectangular ink boxes per step | Done
A - Frontend | Alan | 9. Frontend Client | 41 | Add recognition preview with Confirm/Edit controls | Done
A - Frontend | Alan | 9. Frontend Client | 42 | Add +Add next step / delete-step controls | Done
A - Frontend | Alan | 9. Frontend Client | 43 | Build 'Check my working' action, render feedback + hints | Not Started | Can build against mocked API first
A - Frontend | Alan | 9. Frontend Client | 44 | Add Clear action + client-side state management | Not Started
A - Frontend | Alan | 10. Integration | 45 | Connect frontend to real backend endpoints (replace mocks) | Not Started | Depends on B's endpoints live
A - Frontend | Alan | 10. Integration | 46 | Test full end-to-end flow with Jeff | Not Started | Depends on #45
A - Frontend | Alan | 10. Integration | 46b | Handle network/error states in UI (recognition failure, timeout) | Not Started
Alan
Jeff
Richard
|  |  |  | Actions | Next Meeting
|  |  |  | 1. Define DoD/Deliverables. | 2.Aug
|  |  |  | 2. Break down to tasks. | 2.Aug
|  |  |  | 3. Review each other to be sure we aligned on expecations. | 2.Aug
4. Impl.
| Goal of 1st MVP | 22.Aug

## Dashboard
Owner | Total Tasks | Not Started | In Progress | Blocked | Done
Dev A | 0 | 0 | 0 | 0 | 0
Dev B | 5 | 5 | 0 | 0 | 0
Dev C (Leader) | 1 | 1 | 0 | 0 | 0
Dev B + C | 0 | 0 | 0 | 0 | 0
All (led by C) | 1 | 0 | 1 | 0 | 0
All | 12 | 11 | 1 | 0 | 0
TOTAL | 19 | 17 | 2 | 0 | 0